BA 352									1/20/20

Today				Wednesday			Friday

“Crashing”			Crashing with Solver		ICEs 1 and 2

Start ICE 2

- Discuss Assignment 1

- Discuss ICE 1

PERT/CPM Crashing

Why speed up?

- Can earn a bonus?

- Or, to catch up and meet deadline is behind schedule, avoid penalties.

- https://www.youtube.com/watch?v=qQB2NXfJev0

How can we speed up a project at minimum cost?

- Overtime: costs time and a half.

- Hire extra labor, rent additional equipment.

- Subcontract.

- All have limits and typically cost more than doing yourself.

Example:

Act	I.P.	Norm 	Crash	Cost

A	---	8	5	$750

B	---	12	8	$800

C	---	16	10	$650

D	A	6	4	$500

E	A,B	7	5	$700

F	D	4	3	$400

- How long does this project take under normal conditions?

- How much would it cost to decrease the completion time by one day?

- Two days?

- Four days?

- What is the absolute minimum completion time and what will it cost?

- What assumptions are in place here?  Are they realistic?

- Develop an algorithm for crashing by n days and for finding the minimum completion time/cost.