BA 352								1/27/20

Today			Wednesday		Friday

PERT			More PERT		ICE 3

- Assignment deadlines.

- Discuss ICEs 1 & 2.

- Show reading on PERT/CPM online.

So far:  CPM (Schedule and Scope) and crashing (Schedule and Budget).

- How long?  Completion time. (Schedule)

- Which steps are critical?  Critical path.

- Can we speed it up?  Crashing

Now:  Factor in that activity times are not constant?  PERT (Schedule Uncertainty).

PERT:

- Assume that each activity has an optimistic estimate, a most likely estimate and a pessimistic estimate – three times.

  - Realistic?  Opt and ML yes, Pess???

- Assume each activity follows a Beta distribution.

  - Shape – see Excel file online.

    - Could be Triangle distribution too.  Or Gamma, lognormal???

  - Example:  How long to frame up a typical house?

  - Critique

- Assume the project time is Normal and is completely determined by critical path.

  - Critique

Do example using Normal Approximation:

- For the PERT example in class, what is the distribution of the completion time for the project?

- What is the chance we complete it in 20 days or less?

  - Be realistic

  - Estimate

- What is the chance it takes 30 days or more?

- With 95% (or 99%) certainty, when will it be completed?

PERT Example (We previously did this with just m times):

| Act | I.P. | a (opt) | m (most) | b (pess) | Mean | SD |
| --- | --- | --- | --- | --- | --- | --- |
| A | -- | 4 | 7 | 16 |  |  |
| B | -- | 4 | 5 | 10 |  |  |
| C | A | 8 | 12 | 20 |  |  |
| D | A | 5 | 8 | 12 |  |  |
| E | A | 1 | 2 | 5 |  |  |
| F | B | 3 | 5 | 13 |  |  |
| G | B | 6 | 9 | 24 |  |  |
| H | D | 7 | 9 | 12 |  |  |
| I | E,F | 5 | 6 | 10 |  |  |
| J | G,I | 5 | 7 | 14 |  |  |

- How do you estimate the mean time and SD for each activity?

- What is the mean completion time and critical path?

- Project completion time distribution?

- Probability estimate for finishing early (20 days or less) or late (30 days or more)?

- When are we 95% or 99% certain to complete the project?

Properties of a Beta distribution:

Mean = µ ≈ (a + 4m + b)/6.

SD = σ ≈ (b-a)/6