## Sheet1
ICE 7 Problem 1
| Act. | I.P. | Norm Time | Crash Time | Difference | Cost / Day | Days Crashed
| A | -- | 9 | 5 | 4 | 750 |  |  | Norm Time is how long activity will take under normal conditions.
| B | -- | 5 | 3 | 2 | 600 | 2 |  | Crash Time is the fastest we can get activity done.
| C | B | 6 | 3 | 3 | 1250 |  |  | Difference is how many days we can crash an activity.
| D | B | 9 | 6 | 3 | 900
| E | A,C | 5 | 4 | 1 | 800 | 1 |  | Try changing yellow cells in Days Crashed column and see what effect that has on completion time and cost.
|  | Paths | Regular Time | Max Crash |  |  | Crash
|  | AE | 14 | 9 |  |  | 13
|  | BCE | 16 | 10 |  |  | 13
|  | BD | 14 | 9 |  |  | 12
Cost
|  | Project | 16 | 10 |  |  | 13 |  | 2000
Project takes 16 days under normal conditions, can be done in as little as 10 days.
[11 empty] | 9 | E | 13
|  |  |  | 0 | A | 9 |  |  |  |  | 9 | 4 | 13
|  |  |  | 0 | 9 | 9
|  | Start | [5 empty] | 3 | C | 9 |  |  |  | End
[8 empty] | 3 | 6 | 9
|  |  |  | 0 | B | 3
|  |  |  | 0 | 3 | 3 |  | 3 | D | 12
[8 empty] | 4 | 9 | 13