BA 353: Operations Management						3/20/19

Today			Friday

PERT/CPM		Finish ICEs 6 and 7

Probabilities

- Discuss ICE 6, due Friday 3/22.

| Act | I.P. | Time | SD |
| --- | --- | --- | --- |
| A | -- | 6 | 1 |
| B | -- | 8 | 2 |
| C | A | 5 | 1 |
| D | A | 7 | 2 |
| E | B | 2 | 0.5 |
| F | B | 6 | 1.5 |
| G | C | 5 | 1 |
| H | D, E | 4 | 1 |
| I | F | 4 | 1.5 |
| J | G, H | 6 | 2 |

Project “Ball Park” Probabilities

- Reality:  Activity times are random, not constant.

- Thus, the total project completion time, T, is random.

- May finish early (bonus!), on time, or late (penalty.)

Goals:

- Estimate the probability of finishing on time (or early or late).

- Estimate with 95% or 99% certainty when the project will be done.

Ex:	New column of data:  Standard Deviation

- Activity A takes about 6 ± 1 days, etc.

- Normal???

- Previous result assuming constant times the completion time was 23 days and the critical path was A-D-H-J.

- Let T be the total completion time.  How does T vary?

Assumptions:

- T is normally distributed.

- Use only the critical path.

- μT  = 23

- σT = ………………………

Answers:

- P(T ≤ 19 days) = ………… ≈ 10%

- P(T ≥ 25 days) = ………… ≈ 26%

- P(on time) ≈ 64%

- 95% certain the project will be done in x = μT + z σT.