BA 353: ICE 11

| Act | I.P. | Time | SD |
| --- | --- | --- | --- |
| A | -- | 5 | 1.5 |
| B | -- | 10 | 3 |
| C | -- | 13 |  |
| D | A | 9 |  |
| E | A | 3 |  |
| F | D | 3 |  |
| G | E, B | 8 |  |
| H | C | 9 |  |
| I | F | 4 |  |
| J | D, G | 7 |  |

The data in the table is from the second problem of ICE 8.  Assume that the standard deviation of each activity is 30% of the activity time; so for A, the standard deviation is 30%*5 = 1,5, for B, the standard deviation is 30%*10 = 3, etc.

Simulate this network’s completion time at least 2500 times in Excel and then estimate the answers below.  First you will have to draw the network to identify all the paths through the network, I believe there are five of them.

a) What is the average completion time?  __________

b) What is the standard deviation?  ___________

c) What percent of the time is the project completed in 21 days or less?  __________

d) What percent of the time does the project take 28 days or more?  __________

e) The project will be completed with 99% certainty in how many days?  __________

Parts f) and g) may not be as straightforward as a) – e).  Give them your best shot and get help on them if you need it!

f) Graph and print a cool graph that displays the distribution of the completion times.

g) According to your simulation, what percentage of the time does each path through the network become the critical path? (This might be trickier than it sounds.)