Project Simulation

| Act | I.P. | Time | SD |
| --- | --- | --- | --- |
| A | -- | 6 | 1 |
| B | -- | 8 | 2 |
| C | A | 5 | 1 |
| D | A | 7 | 2 |
| E | B | 2 | 0.5 |
| F | B | 6 | 1.5 |
| G | C | 5 | 1 |
| H | D, E | 4 | 1 |
| I | F | 4 | 1.5 |
| J | G, H | 6 | 2 |

The table on the right is the data for the first PERT/CPM network we discussed in class, which had a completion time of 23 days and critical path A-D-H-J.  However, we now factor in that the completion time for each activity is random with the standard deviation (SD) column.

- Estimate the chance that we’ll be done in 19 days or less.

- Estimate the chance that the project will take 25 days or more.

- With 95% certainty, when will the project be done?

|  | Simulation Estimate |
| --- | --- |
| Completion Time, μT |  |
| Standard Deviation, σT |  |
| P(19 days or less) = |  |
| P(25 days or more) = |  |
| 95% Certain to be done? |  |

Paths from Start to End are:

- ACGJ

- ADHJ

- BEHJ

- BFI